## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Fathima Hasna A | 2026-07-04 | Login page allowed access without proper session validation. | Sprint 1 | Fathima Hasna A | Logical | Added session validation and protected routes. | 2026-07-04 | Closed | Authentication verified successfully.
2 | Fathima Hasna A | 2026-07-06 | File upload accepted unsupported file types. | sprint 1 | Fathima Hasna A | Standards | Restricted uploads to .java and .py files. | 2026-07-06 | Closed | File validation tested successfully.
3 | Fathima Hasna A | 2026-07-08 | Empty code submission displayed no validation message. | Sprint 1 | Fathima Hasna A | Logical | Added empty code validation and improved error messages. | 2026-07-08 | Closed | Validation working correctly.
4 | Fathima Hasna A | 2026-07-10 | React could not communicate with Spring Boot API due to CORS issue. | sprint 1 | Fathima Hasna A | Logical | Configured CORS and tested API connectivity. | 2026-07-10 | Closed | Frontend and backend integrated successfully.
5 | Fathima Hasna A | 2026-07-12 | AI review request returned validation error during testing. | Sprint 1 | Fathima Hasna A | Logical | Updated request handling and review API integration. | 2026-07-12 | Closed | AI review functioning correctly.
6 | Fathima Hasna A | 2026-07-13 | MySQL database connection failed due to configuration issue. | Sprint 1 | Fathima Hasna A | Maintainability | Corrected database configuration and verified connection. | 2026-07-13 | Closed | Database connected successfully.
7 | Fathima Hasna A | 2026-07-14 | AI review page displayed outdated results after code changes. | Sprint 1 | Fathima Hasna A | User Interface | Refreshed API integration and updated frontend logic. | 2026-07-14 | Closed | Latest review results displayed correctly.
8 | Fathima Hasna A | 2026-07-15 | Code Analysis Agent did not detect all coding issues initially. | sprint 1 | Fathima Hasna A | Logical | Improved detection rules and added additional test cases. | 2026-07-15 | Closed | All planned code analysis tests passed.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others